## Context and Objective
ESTABLISHING THE CONTEXT
What is our objective?
<Add objective>
SWOT Analysis
Internal | Strengths | Weaknesses
External | Opportunities | Threats
Note on D7: Tarni McKay: Track record (similar successes) Resource availability Skill levels Processes and systems Reputation
Note on F7: Tarni McKay: Gaps in knowledge and expertise Timescale and deadlines Budget and funding Competing projects Processes and systems
Note on D19: Tarni McKay: Technology and infrastructure development Changing consumer behaviour Emerging and developing markets New innovations (R&D) Market demand
Note on F19: Tarni McKay: Political influences Environmental factors Competitor activity Economy Seasonal effects

## Risks
Risk Register <Project Name> | [10 empty] | Created on: <date created> Last Updated: <date updated> Updated by: <updated by> Version: <version>
Risk Number | Related Issue, Dependency & Assumption Numbers | Raised By | Open/ Closed | Risk Category | Threat/ Opportunity | Risk / Cause / Description | Effect | Proximity | Consequence Rating | Likelihood Rating | Level of Risk | Risk Treatment Strategy | Risk Treatment Description | Risk Owner | Risk Actionee | Due Date for Execution of Risk Treatment Option/s | Stakeholders | Status Updates (Date and Commentary)
SA-BN001
SA-BN002
SA-BN004
OA-BN001 | BN001 - BN003 | [15 empty] | BQ executive, PD, TMR & Translink senior officers.
OA-BN002
OA-BN003
DBC-BN001
DBC-BN002
DBC-BN003
DBC-BN004
DBC-BN005
DBC-BN006
DBC-BN007
DBC-BN008
DBC-BN009
DBC-BN010
DBC-BN011
Note on T3: MA: Status updates should be recorded for the risk when: The risk is registered; A decision is made on the risk treatment option/s; Treatment is commenced; Treatment is completed; The risk is reviewed; The risk is escalated to the Project Board; The person or team who raised the risk and/or affected stakeholders are updated on the status of the risk and/or its treatment; The risk is realised and an issue is raised in the Issue Register; The risk is closed; The risk is transferred to the next stage of the project for continued management (at the end of the current project stage and a new Risk Register is to be established for the next project stage); or The risk is transferred to an external party to be managed (at the end of a project stage or the end of the project).
Note on B4: Strategic Assessment
Note on B7: Options Analysis
Note on B10: Detailed Business Case

## Project Owner (hidden)
[9 empty] | Initial Assessed Risk Rating | [10 empty] | Residual Risk Rating |  |  | Net Financial Impact
Risk Number | Related Issue, Dependency & Assumption Numbers | Raised By | Open/Closed | Risk Category | Threat/ Opportunity | Cause / Description | Effect | Proximity | Consequence Rating | Likelihood Rating | Level of Risk | Risk Treatment Strategy | Risk Treatment Description | Approved By | Risk Owner | Risk Actionee | Due Date for Execution of Risk Treatment Option/s | Stakeholders | Status Updates (Date and Commentary) | Consequence Rating | Likelihood Rating | Level of Risk | Best Case | Most Likely Case | Worst Case
BN001 | BN001 - BN003 |  | Closed | Governance | Threat | Terms of reference for the Project Steering Committee not agreed between parties. | * Business Performance and capability, can be rectified over a 3 month period. Moderate impediment to achieving objectives. * Project outcomes not realised * Schedule delay 10-20% * Occasional negative media attention * Minor local community concerns * Significant impact on budget <5% | Within Stage | Major | Possible | Medium | Reduce | * Informal communications channels * Project coordination group * PAF * IIC * Project schedule and control points * Risk management Agree membership of PSC and develop ToR |  | Executive Director (Rail Performance, Contracts and Operations) | Paul Lange | 2015-03-31 | * PIP * TSP * TransLink * PDO * Government | Risk treatment completed - Steering Committee established and Terms of Reference agreed. | Minor | Unlikely | Minor
BN002 | BN001 - BN003 |  | Closed | Governance | Threat | Terms of reference for the Project Steering Committee are unclear. | * Business Performance and capability, can be rectified over a 3 month period. Moderate impediment to achieving objectives. * Project outcomes not realised * Schedule delay 10-20% * Occasional negative media attention * Minor local community concerns * Significant impact on budget <5% | Within Stage | Moderate | Possible | Low | Reduce | [6 empty] | Risk treatment completed - Steering Committee established and Terms of Reference agreed | Minor | Unlikely | Minor
BN003 | BN001 - BN003 |  | Closed | Governance | Threat | Project Steering Committee membership is not fit for purpose. | * Business Performance and capability, can be rectified over a 3 month period. Moderate impediment to achieving objectives. * Project outcomes not realised * Schedule delay 10-20% * Occasional negative media attention * Minor local community concerns * Significant impact on budget <5% | Within Stage | Major | Unlikely | Low | Reduce | [6 empty] | Risk treatment completed - Steering Committee established and Terms of Reference agreed | Minor | Unlikely | Minor
BN004 |  |  | Closed | Financial / Commercial | Threat | * Modelling assumptions (BaT and Northern service connections). * Provision of future Opex/Capex costs by QR in to Business Case. * Timely provision of accurate data * Inadequate funding to conduct detailed analysis in Business Case development * Over estimation of bus operations | [6 empty] | * Technical working group * Peer review of assumptions * Escalate issues to Project Steering Committee * Stakeholder engagement strategyBroaden parameters of economic assessment - reliability - over crowding - accessibility Undertake sensitivity/ scenario analysis |  | Frances Adams |  | 2015-06-30 | * QR * MPs * Customers, road and rail users * Industry * Government, Federal/State /Council
[5 empty] | Opportunity | Bridge clearance at Tibrogargan creek is insufficient for construction vehicles
[26 empty] | minor | 1
[26 empty] | major | 444
Note on A2: MA: The unique reference number for the risk
Note on B2: MA: The unique reference number/s for any related issue, dependency and/or assumption
Note on C2: MA: The name of person or team who raised the risk
Note on D2: MA: Indication of whether the risk is 'Open' or 'Closed'
Note on E2: MA: The category determined for the risk
Note on F2: MA: Indication of whether the event will have a negative (i.e. Threat) or positive (i.e. Opportunity) effect on the project's objectives
Note on G2: MA: The description of the cause of the risk (i.e. the event that needs to occur for the risk to have an impact on the project's objectives)
Note on H2: MA: The description of the effect (i.e. the outcome or impact) that the risk will have on the project's objectives should the event occur
Note on I2: MA: The proximity category determined for the risk (i.e. Imminent, Within Stage, Within Project or Beyond Project)
Note on J2: MA: The consequence rating determined for the risk (i.e. Negligible, Minor, Moderate, Major or Severe)
Note on K2: MA: The likelihood rating determined for the risk (i.e. Rare, Unlikely, Possible, Likely or Almost Certain)
Note on L2: MA: The risk level assessed for the risk (i.e. Low, Medium, High or Very High) based on its determined consequence and likelihood
Note on M2: MA: The risk treatment strategy selected to respond to the risk (i.e. Avoid, Reduce, Fallback, Transfer, Accept, Share, Exploit, Enhance or Reject)
Note on N2: MA: The unique reference number for the risk
Note on O2: MA: The level of management that made the decision (i.e. Project Manager, Project Director, Project Board or Steering Committee) on the selected risk treatment
Note on P2: MA: The name of the person assigned responsibility for managing, monitoring and controlling all aspects of the risk, including implementation of the selected risk treatment option/s
Note on Q2: MA: The name of the person assigned to carry out actions ion the selected risk treatment option/s
Note on R2: MA: The due date for execution of the selected risk treatment option/s
Note on T2: MA: Status updates should be recorded for the risk when: The risk is registered; A decision is made on the risk treatment option/s; Treatment is commenced; Treatment is completed; The risk is reviewed; The risk is escalated to the Project Board; The person or team who raised the risk and/or affected stakeholders are updated on the status of the risk and/or its treatment; The risk is realised and an issue is raised in the Issue Register; The risk is closed; The risk is transferred to the next stage of the project for continued management (at the end of the current project stage and a new Risk Register is to be established for the next project stage); or The risk is transferred to an external party to be managed (at the end of a project stage or the end of the project).
Note on U2: MA: The consequence rating determined for the risk (i.e. Negligible, Minor, Moderate, Major or Severe)
Note on V2: MA: The likelihood rating determined for the risk (i.e. Rare, Unlikely, Possible, Likely or Almost Certain)
Note on W2: MA: The risk level assessed for the risk (i.e. Low, Medium, High or Very High) based on its determined consequence and likelihood

## Risk Scales
RISK ASSESSMENT SCALES
1. Consequence Scale
Indicates the impact of the risk on the objective.
Consequence Level | Impacts the quality of the deployed system | Impacts the cost of delivering the release | Impacts the timeframe for delivery of the release
5 Critical | Unacceptable impact (I.e. system cannot be deployed if risk realised): - application useability - system maintainability - reliability of data - business case benefit - ability to meet regulatory requirement or date | Increase of =>10% of current budget | Slippage by => 6 months of the project critical path
4 Severe | Severe impact (I.e. system could be deployed if risk realised but its success would be jeopardised): - application useability - system maintainability - reliability of data - business case benefit - ability to meet regulatory requirement or date | Increase of =>5% of current budget | Slippage by => 3 months of the project critical path
3 Major | Major impact (I.e. system could be deployed if risk realised but its success would be reduced): - application useability - system maintainability - reliability of data - business case benefit - ability to meet regulatory requirement or date | Increase of =>3% of current budget | Slippage by => 1 months of the project critical path
2 Serious | Serious impact (I.e. system could be deployed if risk realised but there would be some negative results) - application useability - system maintainability - reliability of data - business case benefit - ability to meet regulatory requirement or date | Increase of =>2% of current budget | Slippage by => 3 weeks of the project critical path
1 Moderate | Significant impact (I.e. system could be deployed if risk realised but there would be minor negative results) - application useability - system maintainability - reliability of data - business case benefit - ability to meet regulatory requirement or date | Increase of =>1% of current budget | Slippage by => 1 week of the project critical path
2. Likelihood Scales
Provides an assessment of the likelihood of the risk occurring.
Likelihood | Description
1 Rare | May occur only in exceptional circumstances
2 Unlikely | Could occur at some time
3 Possible | Might occur at some time
4 Likely | Will probably occur in most circumstances
5 Almost Certain | Is expected to occur in most circumstances (at least once a year)
3. Consequence Scale
Consequence Level | Impacts the quality of the deployed system | Impacts the cost of delivering the release | Impacts the timeframe for delivery of the release
5 Severe | Unacceptable impact (I.e. system cannot be deployed if risk realised): - application useability - system maintainability - reliability of data - business case benefit - ability to meet regulatory requirement or date | Increase of =>20% of current budget | Slippage by => 3 months of the project critical path
4 Major | Major impact (I.e. system could be deployed if risk realised but its success would be reduced): - application useability - system maintainability - reliability of data - business case benefit - ability to meet regulatory requirement or date | Increase of =>10% of current budget | Slippage by => 2 months of the project critical path
3 Moderate | Serious impact (I.e. system could be deployed if risk realised but there would be some negative results) - application useability - system maintainability - reliability of data - business case benefit - ability to meet regulatory requirement or date | Increase of =>5% of current budget | Slippage by => 1 months of the project critical path
2 Minor | Minor impact (I.e. system could be deployed if risk realised but there would be minor negative results) - application useability - system maintainability - reliability of data - business case benefit - ability to meet regulatory requirement or date | Increase of =>2% of current budget | Slippage by => 1 week of the project critical path
1 Negligible | Minimal impact (I.e. system could be deployed if risk realised but there would be minor negative results that would be hard to measure) - application useability - system maintainability - reliability of data - business case benefit - ability to meet regulatory requirement or date | Increase of =>1% of current budget | Slippage by => 1 day of the project critical path

## Risk Impact Matrix
INHERENT RISK IMPACT (CONSEQUENCE AND LIKELIHOOD TABLE)
| Consequence Scale: | Indicates the impact of the risk on the objective.
| Likelihood Scale: | Provides an assessment of the likelihood of the risk occurring.
| Risk Impact: | Minor 1 - 5 | Will be managed by the project
Low 6 - 9
Medium 10-14
High 15-19
|  | Critical 20-25 | Will be reported to the project steering committee
LIKELIHOOD
|  | 1 Rare | 2 Unlikely | 3 Possible | 4 Likely | 5 Almost Certain
CONSEQUENCE | 5 Severe | 5 | 10 | 15 | 20 | 25
| 4 Major | 4 | 8 | 12 | 16 | 20
| 3 Moderate | 3 | 6 | 9 | 12 | 15
| 2 Minor | 2 | 4 | 6 | 8 | 10
| 1 Negligible | 1 | 2 | 3 | 4 | 5

## Validation
VALIDATION
Risk Number | Related Issue, Dependency & Assumption Numbers | Raised By | Open/Closed | Risk Category | Threat/Opportunity | Cause | Effect | Proximity | Consequence Rating | Likelihood Rating | Level of Risk | Risk Treatment Strategy | Risk Treatment Description | Approved By | Risk Owner | Risk Actionee | Due Date for Execution of Risk Treatment Option/s
|  |  | Open | Project Owner | Threat |  |  | Business Case | Negligible | Rare |  | Avoid
|  |  | Closed | Financial / Commercial | Opportunity |  |  | Project | Minor | Unlikely |  | Reduce
|  |  | Rejected | Legal |  |  |  | Beyond Project | Moderate | Possible |  | Fallback
|  |  | Merged | Industrial Relations |  |  |  |  | Major | Likely |  | Transfer
|  |  | Deferred | Legislative |  |  |  |  | Severe | Almost Certain |  | Accept
|  |  |  | Technical | [7 empty] | Share
|  |  |  | Governance | [7 empty] | Exploit
|  |  |  | Implementation | [7 empty] | Enhance
|  |  |  | Planning | [7 empty] | Reject
External Stakeholders
Design
Construction
Commissioning
Transition
Safety
Environmental
Operation
Decommissioning
Consequence Rating |  | Likelihood Rating
Negligible | 1 | Rare | 1
Minor | 2 | Unlikely | 2
Moderate | 3 | Possible | 3
Major | 4 | Likely | 4
Severe | 5 | Almost Certain | 5
Impact
1 | Minor
2 | Minor
3 | Minor
4 | Minor
5 | Minor
6 | Low
7 | Low
8 | Low
9 | Low
10 | Medium
11 | Medium
12 | Medium
13 | Medium
14 | Medium
15 | High
16 | High
17 | High
18 | High
19 | High
20 | Critical
21 | Critical
22 | Critical | [9 empty] | Project Owner | Construction
23 | Critical | [9 empty] | Financial / Commercial | Design
24 | Critical | [9 empty] | Legal | Environmental
25 | Critical | [9 empty] | Industrial Relations | External Stakeholders
[11 empty] | Legislative | Financial / Commercial
[11 empty] | Technical | Governance
[11 empty] | Governance | Legal
[11 empty] | Implementation | Legislative
[11 empty] | Planning | Planning
[11 empty] | External Stakeholders | Safety
[11 empty] | Design | Technical
[11 empty] | Construction | Implementation
Commissioning
Transition
Safety
Environmental
Operation
Decommissioning